## List
number | Requirements | category | module | Man-day | pgm count | Standard program code (reference) | Site additional development program code (reference) | note | Check logic
1 | [Detailed performance inquiry (tally) by budget subject_park] 1. Modified so that the initial budget for one year is displayed in the initial budget. | correction | Accouting | 2 | 1 | 500892 | 72220093 | Just change the sp modification logic a little bit.
2 | [Foreign currency evaluation] 1. Additional development so that foreign currency deposit evaluation can be done on a daily basis 2. Additional development so that foreign currency deposit evaluation (reduction evaluation) can be done on a daily basis | new | Accouting | 8 | 2 | 500971 500972 |  | Site table by date required - _TACSttlDepoRate
3 | [Profit and loss statement (by cost center)] 1. Additional development to view the profit and loss statement by cost center in the same way as the budget | new | Accouting | 5 | 1 |  | 72220090 | You can create it by copying it from the existing screen.
4 | [Create corporate card usage details accounting slip] 1. Additional development so that accounts such as entertainment expenses/vehicle maintenance expenses are not applied to VAT on the corporate card usage history accounting slip creation and corporate card usage history accounting slip creation (individual) screen. | new | Accouting | 4 |  | 521050 521133 |  | Account definition, customer consultation / Lua script modification
5 | [Monthly Statement of Financial Position] 1. Additional development of inquiry chart by amount unit | new | Accouting | 2 | 1 | 500563 |  | Add search conditions / Decimal places to be truncated by agreement with customer
6 | [Export sales processing] 1. When processing export sales, calculate by applying the average exchange rate of export sales and advance payment 2. Apply exchange rate after selecting advance payment ※ Detailed formula needs to be checked during development | new | Export | 4 | 1~2 | 501046 |  | Dialog screen provided / Calculation method
10 | [Customer registration] 1. Development of approval process for customer registration 2. Creation of customer data upon final approval of customer registration request, customer registration request status, payment document, and payment document | new | Sales | 13 | 3 | 527412 527413 |  | _TDACustReq _TDACustReqKind _TDACustReqUserDefine/it Developed with reference to control
11 | [Electronic tax invoice (regularly issued)] 1. Additional development so that electronic tax invoices cannot be transmitted for cases without slip approval | new | Sales | 2 | 1 | 501218 |  | Add check logic
12 | [Employee Multiple Search] 1. Enhancement of the screen for employee multiple search 2. Developed to search by organization level | new | Payroll | 4 | 1 |  |  | 1. Need to organize additional multi-search items 2. Need detailed UI to display at organizational level | select umdeptlevel,* from _THROrgDept select * from _tdauminor where majorseq = 3054
14 | [Holiday work application] 1. When the holiday work request is approved, add the number of vacation days in other vacation items and manage the date. | new | Payroll | 2 | 1 | 2720642 |  | Attendance items Define other work categories _TXPRWkEtcMng Put it in the screen standard column Define use start date Use end date Define customer company Confirmation management Post-processing SP site development required
15 | [Application for working hour adjustment] 1. Development of working hour adjustment application process 2. Application for working hour adjustment (individual), inquiry of working hour adjustment application details (individual), inquiry of working hour adjustment application details (administrator), approval document, final approval document Data reconciliation upon approval | new | Payroll | 15 | 4 |  |  | 526009 526074 _TXPRWkFlexWorkApp _TXPRWkFlexWorkAppSchedule Two-screen reference /Payment document form required/ After treatment Attendance tally table needs to be updated
16 | [Work history status_park] 1. Upgraded by considering work application/overtime work/holiday work/overtime work, etc. based on work history status ※ Detailed specifications need to be discussed | correction | Payroll | 6 | 1 |  | 72220004 | Rules need to be clear. List which attendance items to use as a standard.
17 | [Work Application] 1. Indicate start/end time on the work application approval screen | correction | Payroll | 1 | 1 | 523017 523018 |  | SP modification and design modification /Customer design and location consultation
26

## 근태조회 분석-No.16
근태조회 분석1 | 근태조회 분석2
'- 근무신청(외근, 출장, 교육) 승인될 경우 해당 시간 출퇴근 시간에 자동으로 입력 되도록 개선 필요 - 이 경우 출근 및 퇴근 시간 표시되는 방식은 아래와 같음 <출근시간 표시> SECOM 당일 첫 TAG한 시간 ERP에서 출근 체크한 시간 근무신청서(외근, 국내출장, 해외출장, 교육 등)상 시작 시간 위의 시간 중 가장 빠른 시간을 출근시간으로 표시 => select * from _TPRWkItem where SMWkAppSort = 5011005 select * from _TPRWkEmpDd as a join ( select wkitemseq from _TPRWkItem where SMWkAppSort = 5011005) as b on b.wkitemseq = a.wkitemseq --근무 신청 select * from _TXPRWkWorkApp -- 외근, 출장, 교육 select * from _TXPRWkWorkAppDtl -- get the early time --confirm value join with upper _TXPRWkWorkApp and condition is cfmcode = '1' select * from _tcomconfirm where confirmseq = 22000009 <퇴근시간 표시> SECOM 마지막으로 TAG한 시간 ERP에서 퇴근 체크한 시간 근무신청서(외근, 국내출장, 해외출장, 교육 등)상 종료 시간 위의 시간 중 가장 늦은 시간을 퇴근시간으로 표시 => select * from _TPRWkItem where SMWkAppSort = 5011005 select * from _TPRWkEmpDd as a join ( select wkitemseq from _TPRWkItem where SMWkAppSort = 5011005) as b on b.wkitemseq = a.wkitemseq --근무 신청 select * from _TXPRWkWorkApp select * from _TXPRWkWorkAppDtl --get the late time --confirm value join with upper _TXPRWkWorkApp and condition is cfmcode = '1' select * from _tcomconfirm where confirmseq = 22000009 연장근무시간 1,005 야간근무시간 1,006 휴일근무시간 1,007 _TXPRWkType -- SMOverTimeOccurSeq select * from _tcacodehelpdata where codehelpseq = 2720108 --근무형태_VEN--_TXPRWkTypeForm select * from _tcacodehelpdata where codehelpseq = 2720104 --일구분_VEN--_TXPRWkDayType select * from _tcacodehelpdata where codehelpseq = 2720108 --근무유형_VEN--_TXPRWkType select * from _TXPRWkTypeForm =>_TXPRWkTypeEmp select * from _TXPRWkDayType select * from _TXPRWkType _TXPRWkTypeTimeSet 확정 시 _TXPRWkOverTimeAppWkKind =>SMWkKindSeq select * from _TXBMsMinor where majorseq = 5037 참고 sp : _SXPRWkPayOverTimeCalc 연장 근무 계산 로직 : _SXPRWkEmpOverTimeCalc=>_TXPRWkOverTimeAppDtl+_TXPRWkTypeTimeSet=>연장 시간 구함 나이스 --사원별 근태유형 _TXPRWkTypeEmp 1. 연장근무시간 계산 로직: ->OTCnt 1)퇴근 간주시간 - 2)출근 간주시간(09:00) - 3)야간휴식시간 1) 퇴근간주시간: MIN(ERP상 퇴근시간 / ERP시간외근무신청 상의 종료 시간 + "00:30") 2) 출근 간주 시간: MAX(ERP상 출근시간, 개인별 정해진 출근 시간) 3) 야간휴식시간 : ERP 상 퇴근시간이 20시 이후인 경우 “- 00:30”, 이전인 경우 “00:00” 으로 계산 select datediff(minute,'2020-01-01 10:30' , '2020-01-02 00:00') _TXPRWkOverTimeApp --연장 근무 --ERP 출근시간,최근시간 _TXPRWkEmpWorkStatus->BegTime,EndTime --출근시간/퇴근시간 select empseq,SMWkKindSeq,DayTypeSeq, BegTime,EndTime from _TXPRWkTypeEmp as a join _TXPRWkTypeTimeSet as b on a.WkTypeSeq = b.WkTypeSeq and WkFormSeq= -1 where b.SMWkKindSeq = 5037002 and DayTypeSeq =1 order by empseq --휴식시간 select empseq,DayTypeSeq, BegTime,EndTime,BreakTimeName,b.* from _TXPRWkTypeEmp as a join _TXPRWkTypeBreakTimeSet as b on a.WkTypeSeq = b.WkTypeSeq and WkFormSeq= -1 where DayTypeSeq =1 order by empseq =>22 시 까지 2. 휴일근무시간 계산 로직: 1) 퇴근 간주시간 - 2)출근 간주시간 - 3) "휴식시간" ->NTCnt select datediff(minute,'2020-01-01 10:30' , '2020-01-02 00:00') 1) ERP 상 퇴근시간 2) ERP 상 출근시간 3) 4시간 근무시 마다 30분씩 차감되도록 해야 함. _TXPRWkEmpWorkStatus->daytypeseq in(2,3,4) 하드코딩 판단 (근무시간+연장근무시간+야간근무시간) select * from _TXPRWkDayType =>SMDayTypeSeq ->1051003 --하드코딩 대신 휴일 select empseq,SMWkKindSeq,DayTypeSeq, BegTime,EndTime from _TXPRWkTypeEmp as a join _TXPRWkTypeTimeSet as b on a.WkTypeSeq = b.WkTypeSeq and WkFormSeq= -1 where WkItemSeq1 in( 1007 --휴일근무시간 ,1008 --휴일연장근무시간 ,1009) --휴일야간근무시간 order by empseq 3. 야간근무시간 계산 로직:시간외근무신청이 있고 22시~06시 사이에 근무한 시간 case 평일일 경우 야간근무 휴일일 경우 야간연장근무 end | select * from _TXPRWkTypeForm --=>_TXPRWkTypeEmp select * from _TXPRWkDayType select * from _TXPRWkType select * from _TXPRWkTypeTimeSet select * from _TXBMsMinor where majorseq = 5037 select empseq,SMWkKindSeq,DayTypeSeq, BegTime,EndTime,b.* from _TXPRWkTypeEmp as a join _TXPRWkTypeTimeSet as b on a.WkTypeSeq = b.WkTypeSeq and WkFormSeq= -1 where b.SMWkKindSeq = 5037002 and DayTypeSeq =1 order by empseq CompanySeq, WkTypeSeq, WkFormSeq, DayTypeSeq, SMWkKindSeq select * from _TXPRWkTypeTimeSet select * from _tdaemp select * from _TXPRWkDayType select * from _tcacodehelpdata where codehelpseq = 2720108 --_TXPRWkTypeForm select * from _tcacodehelpdata where codehelpseq = 2720104 --_TXPRWkDayType select * from _tcacodehelpdata where tablename = '_TXPRWkType' SELECT EnvValue FROM _TXPRWkEnv WHERE CompanySeq = 1 AND EnvSeq = 4 create table #WkEmp( empseq int, WkDate nchar(8) ) insert into #WkEmp select 25,'20220704' SELECT T.WkDate, T.EmpSeq, T.SMWkKindSeq, T.OKMinCnt FROM ( SELECT S.WkDate, S.EmpSeq, S.SMWkKindSeq, S.OKOTMinCnt AS OKMinCnt, S.IsCfm, ISNULL(E.SMOverTimeOccurSeq,0) AS SMOverTimeOccurSeq, ISNULL(E.SMOverTimeTypeSeq,0) AS SMOverTimeTypeSeq FROM ( SELECT ROW_NUMBER() OVER(PARTITION BY A.WkDate, A.EmpSeq, A.SMWkKindSeq ORDER BY A.WkDate, A.EmpSeq, C.AppDate DESC, A.OTAppSeq DESC, A.Seq DESC) AS IdxNo, A.WkDate, A.EmpSeq, A.SMWkKindSeq, A.OKOTMinCnt, A.OTAppSeq, A.Seq, C.IsCfm FROM #WkEmp AS B JOIN _TXPRWkOverTimeAppWkKind AS A WITH(NOLOCK) ON B.WkDate = A.WkDate AND B.EmpSeq = A.EmpSeq JOIN _TXPRWkOverTimeApp AS C WITH(NOLOCK) ON A.CompanySeq = C.CompanySeq AND A.OTAppSeq = C.OTAppSeq WHERE A.CompanySeq = @CompanySeq --AND C.IsCfm = '1' ) AS S JOIN _TXPRWkOverTimeAppDtl AS B WITH(NOLOCK) ON S.OTAppSeq = B.OTAppSeq AND S.Seq = B.Seq LEFT OUTER JOIN _TXPRWkOverTimeAppCancel AS B1 WITH(NOLOCK) ON B.CompanySeq = B1.CompanySeq --##01 AND B.OTAppSeq = B1.OTAppSeq LEFT OUTER JOIN _TXPRWkType AS E WITH(NOLOCK) ON B.CompanySeq = E.CompanySeq AND B.WkTypeSeq = E.WkTypeSeq WHERE B.CompanySeq = 1 AND S.IdxNo = 1 AND ISNULL(E.SMOverTimeOccurSeq, 0) = 5053002 -- 시간외근무신청 AND (ISNULL(B.IsCancel,0) <> 1 OR ISNULL(B1.IsCancel,0) <> 1) --##01 ) AS T WHERE T.IsCfm = '1' -- 확정된건

## 근무조정신청서 확정 후처리-no.15
reference pgm : | 27206412720559
ERP 결재 그룹웨어 | _SWCOMGroupWareWkWorkProc
호출 서브 sp | _SXPRWkWorkAppCfm
데이터 적용 내용 :
1.본테이블 확정 컬럼
2.확정 공통테이블 컬럼
집계 sp 수정

## 근무조정신청서 테이블-no.15
select * from _TXPRWkWorkApp -- 외근, 출장, 교육
select * from _TXPRWkWorkAppDtl -- get the early time
| park_TXPRWkCWorkApp | 출퇴근변경 | [6 empty] | park_TXPRWkCWorkAppDtl | 출퇴근변경상세
key | columnname | remark | order | datatype | length | decimal length | null option | TRUE | CompanySeq | 법인내부코드 | 1 | INT | 0 | 0 | FALSE
TRUE | CompanySeq | 법인내부코드 | 1 | INT | 0 | 0 | FALSE | TRUE | WkCSeq | 출퇴근변경코드 | 2 | INT | 0 | 0 | FALSE
TRUE | WkCSeq | 출퇴근변경코드 | 2 | INT | 0 | 0 | FALSE | TRUE | Seq | 일련번호 | 3 | INT | 0 | 0 | FALSE
FALSE | EmpSeq | 사원코드 | 4 | INT | 0 | 0 | TRUE | FALSE | EmpSeq+B41Q38A41:Q42 | 사원코드 | 4 | INT | 0 | 0 | TRUE
FALSE | AppDate | 신청일 | 5 | NCHAR | 8 | 0 | TRUE | FALSE | WkDate | 근무일자 | 6 | NCHAR | 8 | 0 | TRUE
FALSE | WkFrDate | 근무시작일 | 8 | NCHAR | 8 | 0 | TRUE | FALSE | BegTime | 시작시간 | 9 | NCHAR | 4 | 0 | TRUE
FALSE | WkToDate | 근무종료일 | 9 | NCHAR | 8 | 0 | TRUE | FALSE | EndTime | 종료시간 | 11 | NCHAR | 4 | 0 | TRUE
FALSE | AppDays | 신청일수 | 10 | DECIMAL | 19 | 5 | TRUE | FALSE | WkTypeSeq | 근무유형코드 | 12 | INT | 0 | 0 | TRUE
FALSE | DTCnt | 신청시간 | 11 | DECIMAL | 19 | 5 | TRUE | FALSE | WkTeamSeq | 근무조코드 | 13 | INT | 0 | 0 | TRUE
FALSE | MinCnt | 신청분수 | 12 | INT | 0 | 0 | TRUE | FALSE | WkFormSeq | 근무형태코드 | 14 | INT | 0 | 0 | TRUE
FALSE | WkCReason | 변경사유 | 13 | NVARCHAR | 200 | 0 | TRUE | FALSE | DayTypeSeq | 일구분코드 | 15 | INT | 0 | 0 | TRUE
FALSE | IsCfm | 확정여부 | 21 | NCHAR | 1 | 0 | TRUE | FALSE | AppDay | 신청일수 | 16 | DECIMAL | 19 | 5 | TRUE
FALSE | AppEmpSeq | 신청자 | 24 | INT | 0 | 0 | TRUE | FALSE | DTCnt | 시간수 | 17 | DECIMAL | 19 | 5 | TRUE
FALSE | LastUserSeq | 작업자 | 22 | INT | 0 | 0 | TRUE | FALSE | MinCnt | 분수 | 18 | INT | 0 | 0 | TRUE
FALSE | LastDateTime | 작업일시 | 23 | DATETIME | 0 | 0 | TRUE | FALSE | IsCancel | 취소여부 | 27 | NCHAR | 1 | 0 | TRUE
[8 empty] | FALSE | LastUserSeq | 작업자 | 21 | INT | 0 | 0 | TRUE
[8 empty] | FALSE | LastDateTime | 작업일시 | 22 | DATETIME | 0 | 0 | TRUE

## 거래처 승인 출력물 design-No.10
admin pgm
self pgm